## Instructions
Flats Recycling Package
Implementation plan template for improving recycling at flats
Instructions for completing the Project Implementation Plan template
1 | The purpose of this template is to record and itemise specific information relating to the implementation of the flats recycling package and improvements at flats. The template also acts as a checklist to ensure that all relevant actions are considered when designing the improvements.
2 | The sheet titled Implementation Plan OUTLINE lists the information to be included in the Project Implementation Plan template. The information is divided into a number of discrete tasks. Column B lists the specific actions that are required to be addressed when implementing the Flats Recycling Package. Column C provides supporting information relating to the relevant action. N.B. The various actions listed are not necessarily in order. Instead they can be undertaken concurrently.
3 | In the sheet titled Implementation Plan TEMPLATE, Column B lists the actions that are required to be addressed when implementing the Flats Recycling Package. To complete the template, please use columns C onwards (these list the time period over which the improvements are to be implemented) to identify when the actions listed will be addressed and when they will be completed. Where appropriate, please insert comments detailing how you have addressed the actions listed. Please add or delete rows that are/are not applicable to your local authority/ situation.

## Implementation Plan OUTLINE
| Actions | Supporting information
1 | Internal approvals
1.1 | For example, local authority approvals (budgets) or managing agent internal approvals | Ensure that you have enough budget and resources to manage and deliver the Flats Recycling Package to the flats you identify.
2 | Planning for the Flats Recycling Package
2.1 | Appoint project manager | The project manager will lead on ensuring all tasks are assigned and completed on time. This may be a local authority officer or a staff member from the housing provider or managing agent.
2.2 | Appoint project implementation team | Implementing the Package will require input from across your organisation (e.g. comms, operations, housing etc) and other organisation(s). Establishing a project team, identifying roles and assigning responsibilities at an early stage will help ensure you cover all the bases.
2.3 | Agree timetable for implementation | A key task for the project manager will be to draw up a timetable for planning and implementing the Package.
2.4 | Identify key stakeholders | Identify and engage stakeholders from the outset and encourage buy-in through clear communication, liaison and information. Consider the following stakeholders for each site: the local authority waste management team; the collection crew; the housing provider/landlord; managing agent (if there is one); caretakers; resident groups
2.5 | Identify site(s) to be targeted for the Package | This could be done at the start of the project using existing knowledge of the flats.
2.6 | Complete site assessment(s) | Meet with key stakeholders at each site to review the existing rubbish and recycling services, identify any operational issues, and to agree improvements to be made in line with the FRP. See toolkit for a template site assessment form.
2.7 | Document the details of the FRP requirements and get stakeholder sign-off | Use the information from your site assessment to produce an improvement plan for each site. See toolkit for a template improvement plan.
2.8 | Speak to collection company or reprocessor about the acceptance of plastic bags | We recommend allowing residents to use carrier bags to store, transfer and deposit their recycling in. All our evidence (see the report) demonstrated residents do this naturally as it is more convenient than using a reusable bag.
3 | Procurement
3.1 | Procure materials (state when orders to be placed and receipt of delivery). | An organisations procurement policies will most likely dictate the timetable and process for procurement. Consider using a national procurement framework - please note large procurements can take a long time so this must be factored into the plan. For housing providers/managing agents - check the procedure for new containers on site as these may be provided by the local authority.
3.2 | Procure contractor(s) to install all materials i.e signage, bins | Refer to your comms planning for all requirements. Remember to provide a list of locations and block plans to the contractor
4 | Container installation (if providing extra/new bins)
4.1 | Agree specifications for all containers | We recommend reverse-lids for recycling containers. If you use reverse lid bins, ensure the signage is in the correct location. Ensure the aperture is large enough to fit a carrier bag of recyclables in.
4.2 | Organise storage space for containers | In the event that your contractor is not direct delivering to site, you will need space in the area for receiving new containers. You may also need space for bringing in any old containers, prior to them being refurbished/recycled.
4.3 | Appoint distribution team | This may be direct delivered by the supplier or bulked and delivered by the council. Ensure you provide block plans for every site, with the location for new bins clearly marked on the plan.
4.4 | Agree distribution schedule. | Remember to provide a block plan to the contractor. Ensure you are on site or visit soon after, to ensure the bins are placed in the correct location.
4.5 | Agree take back of old containers | If you are replacing existing bins, consider how you will remove the old containers from the site. This could be done by the same contractor delivering new containers
4.6 | Finalise logistics, e.g. collection schedules, container delivery schedules, address lists for containers; ensure that service providers can access buildings. | Liaise with the distribution company, operations, managing agent, caretaker etc to ensure schedules, address lists and access are all ready.
4.7 | Agree and arrange additional collections | Additional collections may have cost implications, so ensure you have agreed this with the budget holder. Ensure the collection crew schedules are updated.
4.8 | Update collection schedules | Ensure the local authority's waste contractor has up to date collection schedules to account for any new bins, including new locations. This is also important to ensure the recycling bins are returned to the correct location.
4.9 | Crew training for reverse lid bins | Ensure the collection crews understand how to empty the reverse-lid recycling bins and that they are provided with any new lid locks.
5 | Communications
5.1 | Develop communication plan. | This should include: background information; a situational analysis; aims and objectives; details of the target audience; campaign branding and key messages; strategic approach; communication methods (including a list of all the campaign activities); planning (scheduling activities and resources as well as budgeting); and how the monitoring and evaluation will be conducted.
5.2 | Tailor the Flats Recycling Package artwork to the local authority | Liaise with the local authority and housing provider corporate comms teams to ensure they are on board from the outset.
5.3 | Finalise matrix of requirements for every piece of comms on all your sites | This can be taken from all the information collected on your site visits
5.4 | Finalise print and production process and suppliers | This includes securing suppliers for the production of leaflets, posters, stickers, Dibond signage
5.5 | Printing and production of communications materials | Ensure you allow for potential varying lead times of the different materials in your plan
5.6 | Recycling, aperture and rubbish bin stickers - approve and sign off artwork | Ensure you have the correct measurements for the recycling and rubbish bin stickers, as well as the aperture stickers
5.7 | Send bin stickers to the bin manufacturer for production (if purchasing new ones) or to your maintenance team if replacing old stickers | Ensure the bin manufacturer knows where to place the aperture stickers. Consider stocking spare stickers as replacements.
5.8 | Update bins with the new bin stickers (if not purchasing new bins) | Ensure the old stickers are removed and the bins thoroughly cleaned and dried, before applying new stickers.
5.9 | Recycling and rubbish bin store signage - approve and sign off artwork | Ensure you liaise with the housing provider or managing agent as this will be fixed to their assets
5.1 | Recycling and rubbish area signage - approve and sign off artwork | Ensure you liaise with the local authority for content and housing provider/managing agent (at each site) for design
5.11 | Rubbish chute signage - approve and sign off artwork | Remember to consider if these are to be Dibond signs or stickers. Dibond signs can not easily be fixed to convex surfaces. Ensure you have the correct measurements and quantity required. Ensure you have permission from the managing agent/landlord to fix to chutes.
5.12 | Large items signage - approve and sign off artwork | These can be placed in chute rooms as well as bin rooms. Liaise with the local authority waste team for detail on what residents should do about bulky waste. Remember to consider the varied sizes required and quantities. Remember to liaise with the managing agent/landlord of each site for approval to fix to their assets.
5.13 | Don't dump your waste here signage - approve and sign off artwork | Ensure you liaise with the managing agent/landlord as to where these should be fixed. You should have the locations plotted on your site block plan
5.14 | Send all signage requirements to the supplier for production | Be very clear on quantity and sizes of each sign you require. Also, agree the material to be printed on in advance. This may differ between signs.
5.15 | Arrange for all signage to be installed | Remember to include site block plans for each separate site. Be very clear where you want each individual sign mounted and how. We advise you should attend each installation to ensure they are mounted as agreed with your stakeholders.
5.16 | Instructional leaflet for residents - approve and sign off artwork | A5, 6 page, leaflet for residents to reinforce how to use their recycling and rubbish services. See Toolkit for instructions on how to modify the template leaflet. Remember to consult with the local authority.
5.17 | Internal posters - approve and sign off artwork | Use internal recycling posters to promote the items that can be recycled from around the home. Remember to consult with the local authority (if required).
5.18 | Send leaflets and posters to be printed | Ensure you have accounted for the lead in time in your project plan.
5.19 | Arrange for distribution of leaflets | We advise you distribute the leaflets at each site on the same day, or soon after any changes to signage and recycling bins. If you distribute the leaflets before any changes and the recycling bins are not in a great condition, residents could be put off using them. Ensure you have arranged for access to the site for whoever is distributing the leaflets.
5.2 | Arrange for posters to be put up at each site | The noticeboards may be locked, so ensure you obtain the key. Liaise with the landlord/managing agent and caretaker. Ensure you have arranged access to all the sites and blocks.
5.21 | Arrange for new tenants to receive the instructional leaflet | Liaise with the housing provider or landlord to inform you when a new tenant moves in, and send them a leaflet. Consider leaving a supply of leaflets at the site office or with a caretaker for distribution.
6 | Monitoring and evaluation
6.1 | Design plan for monitoring activities | Consider regular visits to your sites where you have installed the Package, to ensure the bins, bin areas, signage etc are being kept clean; that the recycling bins are being put back in the correct location; that the recycing bins lids are being locked; that there are no issues with collection; that posters are still visible; and there are generally no waste management issues. This can be divided between the team. We recommend monthly visits.
6.2 | Ongoing monitoring/ quality control ‒ addressing issues as necessary | Ensure the caretaker/managing agent reports missed collections. Speak regularly with key stakeholders, including caretakers and crews, for feedback on the Package.
7 | Ongoing service delivery
7.1 | Bin and bin area cleaning schedule to be implemented | This includes cleaning the apertures and lids on a weekly basis and regular cleaning of the bins and bin areas.
7.2 | Bin maintenance schedule to be implemented | Maintenance is down to the bin owner, so may be the local authority or the managing agent. See template improvement plan for what this entails.
7.3 | Bulky waste to be regularly cleared | Liaise with key stakeholders as to the arrangements for bulky waste clearance and collection at each site.
7.4 | Bin store maitenance | This includes fixing broken lights, dealing with vermin etc

## Implementation Plan TEMPLATE
| Actions | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24
1 | Internal approvals
1.1 | For example, local authority approvals (budgets) or managing agent internal approvals
2 | Planning for the Flats Recycling Package
2.1 | Appoint project manager
2.2 | Appoint project implementation team
2.3 | Agree timetable for implementation
2.4 | Identify key stakeholders
2.5 | Identify site(s) to be targeted for the Package
2.6 | Complete site assessment(s)
2.7 | Document the details of the FRP requirements and get stakeholder sign-off
2.8 | Speak to collection company or reprocessor about the acceptance of plastic bags
3 | Procurement
3.1 | Procure materials (state when orders to be placed and receipt of delivery).
3.2 | Procure contractor(s) to install all materials i.e signage, bins
4 | Container installation (if providing extra/new bins)
4.1 | Agree specifications for all containers
4.2 | Organise storage space for containers
4.3 | Appoint distribution team
4.4 | Agree distribution schedule.
4.5 | Agree take back of old containers
4.6 | Finalise logistics, e.g. collection schedules, container delivery schedules, address lists for containers; ensure that service providers can access buildings.
4.7 | Agree and arrange additional collections
4.8 | Update collection schedules
4.9 | Crew training for reverse lid bins
5 | Communications
5.1 | Develop communication plan.
5.2 | Tailor the Flats Recycling Package artwork to the local authority
5.3 | Finalise matrix of requirements for every piece of comms on all your sites
5.4 | Finalise print and production process and suppliers
5.5 | Printing and production of communications materials
5.6 | Recycling, aperture and rubbish bin stickers - approve and sign off artwork
5.7 | Send bin stickers to the bin manufacturer for production (if purchasing new ones) or to your maintenance team if replacing old stickers
5.8 | Update bins with the new bin stickers (if not purchasing new bins)
5.9 | Recycling and rubbish bin store signage - approve and sign off artwork
5.1 | Recycling and rubbish area signage - approve and sign off artwork
5.11 | Rubbish chute signage - approve and sign off artwork
5.12 | Large items signage - approve and sign off artwork
5.13 | Don't dump your waste here signage - approve and sign off artwork
5.14 | Send all signage requirements to the supplier for production
5.15 | Arrange for all signage to be installed
5.16 | Instructional leaflet for residents - approve and sign off artwork
5.17 | Internal posters - approve and sign off artwork
5.18 | Send leaflets and posters to be printed
5.19 | Arrange for distribution of leaflets
5.2 | Arrange for posters to be put up at each site
5.21 | Arrange for new tenants to receive the instructional leaflet
6 | Monitoring and evaluation
6.1 | Design plan for monitoring activities
6.2 | Ongoing monitoring/ quality control ‒ addressing issues as necessary
7 | Ongoing service delivery
7.1 | Bin and bin area cleaning schedule to be implemented
7.2 | Bin maintenance schedule to be implemented
7.3 | Bulky waste to be regularly cleared
7.4 | Bin store maitenance